## FRONT_PAGE
Product Name | hutbazar | Test Start Date | 27-10-2023 | TC Execution Start Date
Module Name | Front-Page | Test End Date |  | TC Execution End Date
|  | Test Case Developed By | Rakhi | Browser (Tested) | Mozilla Firefox
Product Name |  | Test Case Reviewed By |  | Perfomance (Tested)
Test Executed By
Test Case Id | Test Case Title | Pre Requisite | Test Steps | Test Data | Expected Result | Actual Result | Test Status/Result | Remark | Defect ID
TC_001 | Verify buttons clickable or not in the 'Header - nav section' | Go to the link ( https://hutbazar.com ) | Click on the buttons | Not Applicable | button should be clickable and taken to the related page | button hase been clickable and taken to the related page | Pass
TC_002 | Verify page logo buttons clickable or not in the 'Header section' | Go to the link ( https://hutbazar.com ) | Click on the buttons | Not Applicable | Logo should be clickable and taken to the Home page | Logo has been clickable and taken to the Home page | Pass
TC_003 | Verify search criteria in searchbar with any letter and suggested name with the letter | Go to the link ( https://hutbazar.com ) | 1. Click on the search button 2. Enter any letter on the searchbar | search : r | it should be visiable with all products which start with the letter | it does not show any name which start with the letter | Fail | search.mp4 | df_id_001
TC_004 | Verify place holder text added on search or not in the 'search section' | Go to the link ( https://hutbazar.com ) | 1.Click on the searchbutton 2. Enter any product name on the searchbar | search : beef | it should be visiable with all products which start with the word | it's visiable with all products which start with the word | Pass
TC_005 | Try different search terms and check that the correct results are returned each time | Go to the link ( https://hutbazar.com ) | 1.Click on the search button 2. Enter any word on the searchbar | search1 : gift search2 : rose | it should be visiable with all products which start with the name | it's visiable with all products which start with the name | Pass
TC_006 | Verify an error message display by entering invalid keywords in the search field | Go to the link ( https://hutbazar.com ) | 1.Click on the search button 2. Enter any invalid keywords on the searchbar | search : # | it should be displayed the keywords are not valid | it's visiable with all products which has the symbol | Fail | search.mp4 | df_id_002
TC_007 | Test the search functionality by searching for a term with a mix of upper and lower case letters. | Go to the link ( https://hutbazar.com ) | Click on the search button | search : HearT | it should be visiable with all products which start with the mix up | it's visiable with all products which start with the words | Pass
TC_008 | Verify all Products clickable or not in the 'Featured Products section' | Go to the link ( https://hutbazar.com ) | Click on the product button | Not Applicable | button should be clickable and taken to the related page | button hase been clickable and taken to the related page | Pass
TC_009 | Verify all image size equal or not in the 'Featured Products section' | Go to the link ( https://hutbazar.com ) | 1. Click on the image 2. Inspect the images/product card and measure the size | Not Applicable | images should be equal size | images are not equal size | Fail | https://drive.google.com/file/d/1JrcrPxH6yjKL-liNKzPyNGS-9i_2ZmJr/view?usp=drive_link | df_id_003
TC_010 | Verify all Products clickable or not in the 'Explore Popular Categories section' | Go to the link ( https://hutbazar.com ) | Click on the product button | Not Applicable | button should be clickable and taken to the related page | button hase been clickable and taken to the related page | Pass
TC_011 | Verify all image size egual or not in the 'Explore Popular Categories section' | Go to the link ( https://hutbazar.com ) | 1. Click on the image 2. Inspect the images/product card and measure the size | Not Applicable | images should be equal size | images are not equal size | Fail | hutbazar.mp4 | df_id_004
TC_012 | Verify hover features on th all product cards in the 'Explore Popular Categories section' | Go to the link ( https://hutbazar.com ) | Check the hover function on the cards | Not Applicable | all images should be hovered | all images have not hovered | Fail | explore-hover.mp4 | df_id_005
TC_013 | Verify all Products clickable or not in the 'Recent Additions section' | Go to the link ( https://hutbazar.com ) | Click on the product button | Not Applicable | button should be clickable and taken to the related page | button hase been clickable and taken to the related page | Pass
TC_014 | Verify all image size egual or not in the 'Recent Additions section' | Go to the link ( https://hutbazar.com ) | 1. Click on the image 2. Inspect the images/product card and measure the size | Not Applicable | images should be equal size | images have not equal size | Fail | hutbazar.mp4 | df_id_006
TC_015 | Verify all Products clickable or not in the 'Our Daily Deals section' | Go to the link ( https://hutbazar.com ) | Click on the product button | Not Applicable | button should be clickable and taken to the related page | button hase been clickable and taken to the related page | Pass
TC_016 | Verify all image size egual or not in the 'Our Daily Deals section' | Go to the link ( https://hutbazar.com ) | 1. Click on the image 2. Inspect the images/product card and measure the size | Not Applicable | images should be equal size | images have not equal size | Fail | hutbazar.mp4 | df_id_007
TC_017 | Verify all buttons are clickable or not in 'Footer section' | Go to the link ( https://hutbazar.com ) | Click on the product button | Not Applicable | button should be clickable and taken to the related page | button should be clickable and taken to the related page | Pass
TC_018 | Verify all contact email box and button size egual or not in the 'footer section' | Go to the link ( https://hutbazar.com ) | 1. Click on the product image 2. Inspect the email box and button measure the size | Not Applicable | email box and send button should be equal size | email box and send button has not equal size | Fail | email-button.PNG | df_id_008
TC_019 | Verify all section alignment position | Go to the link ( https://hutbazar.com ) | Inspect the page measure the alignment and check position | Not Applicable | all section name position and alignment should be same | all sections name position and alignment have not same | Fail | hutbazar.mp4 | df_id_009

## AddToCart
Product Name | hutbazar | Test Start Date | 2023-02-11 | TC Execution Start Date
Module Name | Add to Cart | Test End Date |  | TC Execution End Date
|  | Test Case Developed By | Rakhi | Browser (Tested) | Mozilla Firefox
Product Name |  | Test Case Reviewed By |  | Perfomance (Tested)
Test Executed By
Test Case Id | Test Case Title | Pre Requisite | Test Steps | Test Data | Expected Result | Actual Result | Test Status/Result | Remark | Defect ID
TC_001 | Check whether the Cart button is seen on the display page after add to cart a product from the Home page | 1. Go to the link ( https://hutbazar.com ) | click on the 'add button ' | Not Applicable | View Cart button should be seen on the front like modal or pop up | The view cart button is not visible in the foreground. The cart button was stuck in the nav bar. | FAIL | addcart.mp4 | df_id_001
TC_002 | Check success message is displayed or not when a product is added to the cart successfully | 1. Go to the link ( https://hutbazar.com ) | click on the 'add button ' | Not Applicable | success message should be viewed on the front after adding the product to the cart. | There was no success message on the front after adding the product to the cart. It was just a checked symbol on the peoduct. | FAIL | addcart.mp4 | df_id_002
TC_003 | Check whether the Cart button is seen on the product display page | 1. Go to the link ( https://hutbazar.com ) | click on the product details button | Not Applicable | Cart button should be displayed on the product display page | Cart button has been displayed | PASS
TC_004 | Check whether the user can add products to the cart or not | 1. Go to the link ( https://hutbazar.com ) | click on the add button | Not Applicable | user should add the product to their shopping cart. | user can add the product to their shopping cart. | PASS
TC_005 | verify whether the 'view-cart' button is clickable or not and by default checked the checkout | 1. Go to the link ( https://hutbazar.com ) | 1. click on the add button 2. click on the cart button 3. click on the view cart button | Not Applicable | view cart should be clickable | view cart should be clickable | PASS
TC_006 | Verify whether the quantity of the product increases when Adding multiple items to the cart | 1. Go to the link ( https://hutbazar.com ) | 1. click on the product details button 2. click on the add button 3. click on the view cart button | Not Applicable | product quantity should be increased after adding products | product quantity was increased after adding products | PASS
TC_007 | Check whether the total price is added when the product is added to the cart | 1. Go to the link ( https://hutbazar.com ) | 1. click on the product details button 2. click on the add button 3. click on the view cart button | Not Applicable | product price should be increased after adding products | product price was increased after adding products | PASS
TC_008 | Verify whether the total price reduces when the product is removed from the cart with confirmation | 1. Go to the link ( https://hutbazar.com ) | 1. click on the product details button 2. click on the add button 3. click on the view cart button 4. remove the products | Not Applicable | product price should be removed after removing products | product price removed after removing products | PASS
TC_009 | Verify warning message when the product is removed from the cart with a undo option | 1. Go to the link ( https://hutbazar.com ) | 1. click on the add button 2. click on the view cart button 3. remove the products | Not Applicable | a warning message should be seen and displayed a undo button | a warning message seen and displayed a undo button | Pass
TC_010 | Check whether the '+' and '-' button is seen on the view cart page and with the add item | 1. Go to the link ( https://hutbazar.com ) | click on the add button | Not Applicable | '+' and '-' button should be seen with the add item and view cart | '+' and '-' button seen with the add item and view cart | Pass
TC_011 | verify whether the '+' and '-' button is clickable on the view cart page and with the add item | 1. Go to the link ( https://hutbazar.com ) | 1. click on details button 2. click on the add button 3. click on the '+' , '-' button | Not Applicable | '+' and '-' button should be clickable with the add item and view cart | '+' and '-' button was cilckable with the add item and view cart | Pass
TC_012 | verify whether update cart button is clickable on the view cart page | 1. Go to the link ( https://hutbazar.com ) | 1. click on details button 2. click on the add button 3. click on the '+' , '-' button 4. click on the 'update cart' | Not Applicable | update button should be clickable and update the car with modified item | update button was clickable and update the car with modified item | Pass
TC_013 | verify whether '+' , and '-' option is available after update cart button | 1. Go to the link ( https://hutbazar.com ) | 1. click on the product details button 2. click on the add button 3. click on the '+' , '-' button 4. click on the 'update cart' | Not Applicable | '+' , and '-' option should be available after update cart button for more modify item if user want | '+' , and '-' option was not available after update cart button | FAIL | No('+' , '-')Afterupdatedproducts.png | df_id_003
TC_014 | Check the add to cart related product suggestion is seen or not after adding a item to the cart | 1. Go to the link ( https://hutbazar.com ) | click on the add button | Not Applicable | should be displayed related product suggestion after add a item to the cart | there was no suggestion to add like added item | FAIL | addcart.mp4 | df_id_004
TC_015 | Check whether the cart becomes empty when the user clicks on the '-' button when only a single product is present in the shopping cart | 1. Go to the link ( https://hutbazar.com ) | 1. click on the add to cart button 2. click on the cart button 3. click on the view cart 4. click on the '+' , '-' button 5. click on the 'update cart' button | Not Applicable | It should be become empty and displayed a empty message | It became empty and displayed a empty message | Pass
TC_016 | Check whether unregistered users can update Calculate shipping address | 1. Go to the link ( https://hutbazar.com ) | 1. click on the add to cart button 2. click on the cart button 3. click on the view cart 4. enter address information 5. click on updated button | Not Applicable | It should not be updated the address without registration | The shipping address was updated without log in | FAIL | addcart.mp4 | df_id_005
TC_017 | Verify the input box and 'Apply coupon' size in the 'Have A Promotional Code?' section | 1. Go to the link ( https://hutbazar.com ) | 1. click on the add to cart button 2. click on the cart button 3. click on the view cart 4. check the size | Not Applicable | input box and apply coupon button should be equal size | input box and apply coupon button are not equal size | FAIL | addcart.mp4 | df_id_006